## Exteriors
| Eagle Landing Southern Pines |  |  |  | Completed
EXTERIOR FINISHES
LOCATION/DESCRIPTION | DESCRIPTION | COLOR | PHOTO | NOTES
ROOF SHINGLES |  | Barkwood (approved alterante) |  |  | Per dropbox sent 5/1/20
STANDING SEAM METAL | Coastal Metal Service | Teak Brown |  |  | Per dropbox sent 5/1/20
PAINT - (Per Rendering) |  |  |  |  | Per dropbox sent 5/1/20
PAINT - Board and Batten
PAINT - Lap Siding |  |  |  |  | Walls and Trim same as Club and other exteriors. 2.4.21 ok'd
PAINT - Trim |  |  |  |  | White per call 5/28. Bob Koontz to confirm swatches.
PAINT - Doors |  | Brown |  |  | Door color OK'd 2.4.21
BALCONY RAILINGS | X-style per renderings. | Black |  | Alumiworks is the vendor. They will deliver/install with a Finish coat of paint. | Per call on 5/28. Evolve to talk to vendor to and provide options/styles similar to renderings.
OPEN SHUTTER | NA | NA
SITE FENCING | Aluminum - 3 Line, No finials | Black
VENEER STONE/BRICK | Triangle Brick | Harpers Creek |  |  | Samples received 5/20, ZDC reviewing. WB
WINDOWS | Single Hung Vinyl | White Vinyl |  |  | ZDC requests Grid in top only
POOL TILE - WATERLINE | Tiburstone 6x6 CT - TBR 8 Ivory |  |  |  | Bob Koontz/Level 5 once design is complete.
POOL TILE - ACCENT |  |  |  |  | Bob Koontz/Level 5 once design is complete.
POOL COPING | Ivory Tumbled Travertine |  |  |  | Bob Koontz/Level 5 once design is complete.
POOL SHELL FINISH | Aggerate Pool Finish | Ivory |  |  | Bob Koontz/Level 5 once design is complete.
POOL DECK FINISH | Small Salt Finish (like surf city job) |  |  |  | Per Joe and Lowell 2.4.21
MAILBOXES |  | Bronze to match Metal Roof Color |  |  | Per 5/28 call, Evolve to provide options and try to match metal roof color.
SITE POLE LIGHTS | RAB Outdoor - Ivelot | Black w/ Black Poles |  |  | ZDC 11.3.20 selection
CLUB EXTERIOR WALL LIGHTS | Hubbardton Forge and Kichler | See spec |  |  | ZDC 11.12.20 ok from Koontz Jones
FLASHING DETAILS | End Dam flashing below windows
FLASHING DETAILS | Arch Lintel flashing
FLASHING DETAILS | Arch Lintel flashing - end dam
FLASHING DETAILS
FLASHING DETAILS

## CABINETS + COUNTERS
| Eagle Landing Southern Pines |  |  |  |  | Completed
CABINETS + QUARTZ SCHEME A (Gray Cabinets) | SCHEME A | PLAN SPECS | PLAN SPECS | PLAN SPECS
LOCATION/DESCRIPTION | DESCRIPTION | COLOR | PHOTO | NOTES | NOTES | NOTES
KITCHEN CABINETS | United Finishers International, Inc Contemporary Square Recessed Panel Door 42" Wall Cabinets, Full Overlay, | Proper Gray Finish |  |  |  | Approved Shaker Square by Level 5 - Color to be Proper Gray Owner requests raised corner cabinet. Include all crown trim. Instead of a cabinet above the fridge, replace with a wine rack.
KITCHEN HARDWARE | Liberty Hardware - Model #P37280C-FB-CP | Chrome |  | VE - Alternates ok to Submit | 3 3/4" | Per 5/28 call, the descision to go chrome was made.
KITCHEN QUARTZ | Granite - Level 4 | Andromeda White |  | ZDC chose and Ok'd this upgrade 5.21.20 |  | $11,800 was included in final costs to include Level 4 granite in budget.
KITCHEN BACKSPLASH | Standard 3x6 Tile | Bone - Keep this?? |  | ZDC made change 5.18.20 | Glossy, 3x6 Install witih 1/2 Offset | Level 5 to look and confirm Kitchen Backplash per 5/28 call.
Backsplash Grout | Mapei | Mapei 38 Avalanche |  |  |  | Level 5 to look and confirm Kitchen Backplash per 5/28 call.
BATHROOM CABINETS | United Finishers International, Inc Contemporary Square Recessed Panel Door 42" Wall Cabinets, Full Overlay, | Proper Gray Finish |  |  | NO Topper cabinets in baths | Approved Shaker Square by Level 5 - Color to be Proper Gray
BATHROOM HARDWARE | Liberty Hardware - Model #P37280C-FB-CP | Flat Black |  | VE - Alternates ok to Submit |  | Per 5/28 call, the descision to go chrome was made.
BATHROOM QUARTZ | Granite - Level 4 | Andromeda White |  | ZDC chose and Ok'd this upgrade 5.21.20
CABINET + DRAWER HARDWARE | Soft Closure on Drawers and Cabinets |  |  |  |  | Per 5/28 call, the descision to go chrome was made.

## PLUMBING FIXTURES
Eagle Landing Southern Pines
PLUMBING FIXTURES | Scheme A & B |  | PLAN SPECS | PLAN SPECS | PLAN SPECS | Completed
DESCRIPTION | MANUFACTURER | FINISH | MODEL # | PHOTO | NOTES
KITCHEN FAUCET | Olympia | Chrome/Stainless | K-5020 |  |  | Per 5/28 call, the descision to go chrome was made.
KITCHEN SINK | MR | Stainless | 2920S |  | Rectangle Single Bowl. | Stainless
BATHROOM FAUCET | Olympia | Chrome/Stainless | L-6050 |  |  | Per 5/28 call, the descision to go chrome was made.
BATHROOM SINK | MR | White porcelain | U1812
TUB / SHOWER TRIM | Olympia | Chrome/Stainless | T-2370 |  |  | Per 5/28 call, the descision to go chrome was made.
SHOWER TRIM | Olympia | Chrome/Stainless | T-2370 |  |  | Per 5/28 call, the descision to go chrome was made.
ADA HAND HELD SHOWER | Olympia | Arctic Stainless | P-4530 |  |  | Per 5/28 call, the descision to go chrome was made.
SHOWER | Sterling, Ensemble | White | 72131100 |  |  | Per 5/28 call, the descision to go chrome was made.
TUB | Sterling, Ensemble | White | 71101120 |  |  | PRICE - Both 4 pc tub/shower combo, and Tile surrounds for tubs and showers - like we did 1st time at Union 198
TOILET | Sterling, Windham | White | ProForce 403081
TOILET - LID | ProFlo | White | PFTSE2000WH

## LIGHTING FIXTURES
Eagle Landing Southern Pines
LIGHTING FIXTURES - UNITS SCHEME A (Gray Cabinets) | Scheme A |  | PLAN SPECS | PLAN SPECS | PLAN SPECS | Completed
DESCRIPTION | MANUFACTURER | FINISH | MODEL # | PHOTO | NOTES
KITCHEN PENDANTS - A | Kuzco Lighting: 498011CH, 60w Max bulb; 3-3/8" cylinder, 9-7/8" tall | Chrome | 498011CH |  |  | Per 5/28 call, the descision to go chrome was made.
BATHROOM VANITY - B | Progress Lighting - 3 Light Vanity in Chrome and White Opal Glass, 100W - P2159-104; 22" wide | Chrome | P2159-104 |  |  | Per 5/28 call, the descision to go chrome was made.
HALL/FOYER - C, D | Butler Lighting Alternate: Orinoco DPV 1432, 12" Flush Mount, 2x60W medium base - Type C, D, Foyer, Type A Hall | Chrome with Opal Glass | DVP1432CH Orinoco Collection |  |  | Per 5/28 call, the descision to go chrome was made.
CLOSET/LAUNDRY - F | Trans Globe Lighting: ES-LED-30021-8WH - 7.5" | White - LED | 30021-8WH
CEILING FAN (LIVING + BEDROOMS) - E | Butler Lighting Alternate: Craftmade, Connery 48" with Blades and Light Kit - Type CF, Option 2. Blades are Ash/Wenge Wood | Brushed Polished Nickel |  |  |  | Per 5/28 call, the descision to go chrome was made.
TRACK (KITCHEN) - H | EGLO - BUZZ 2 track light | Chrome |  |  |  | Per 5/28 call, the descision to go chrome was made.
RECESSED (DINING) - G | Trans Globe Lighting: ES-LED-30021-8WH - 7.5" | White - LED | 30021-8WH
RECESSED (SHOWER) - C | Trans Globe Lighting: ES-LED-30021-8WH - 7.5" | White - LED | 30021-8WH
EXTERIOR PATIO LIGHT | TransGlobe: 50210BK; 60w Max bulb; 10" tall, 9" wide | Black | 50210BK |  |  | Per 5/28 call, the descision to stay black was made. Evolve to include light at entryways.
CLOSET/LAUNDRY - F | AFX, T5L Series - 18", 33", 42", 48"

## FLOORING
| Eagle Landing Southern Pines |  |  |  | Completed
FLOORING SCHEME A (Gray Cabinets) | SCHEME A |  | PLAN SPECS | PLAN SPECS | PLAN SPECS
LOCATION | MANUFACTURER | STYLE | COLORS | PHOTO | NOTES
ENTRY | Cobalt Surfaces | Katanga Sand Dune K12-802 | Katanga Sand Dune K12-802 |  | 7x48 plank size
KITCHEN | Cobalt Surfaces | Katanga Sand Dune K12-802 | Katanga Sand Dune K12-802 |  | 7x48 plank size
LIVING ROOM | Cobalt Surfaces | Katanga Sand Dune K12-802 | Katanga Sand Dune K12-802 |  | 7x48 plank size
BEDROOM + BEDROOM CLOSETS | Shaw | Go For It | Sandstone - E0322/00720 |  | ZDC - 4.9.20 approved
BATHROOM FLOOR | Cobalt Surfaces | Katanga Sand Dune K12-802 | Katanga Sand Dune K12-802 |  | 7x48 plank size
BATHROOM SURROUNDS | Tile | TBD | TBD | TBD | TBD
BATHROOM SURROUND - ACCENT | Tile | TBD | TBD | TBD | TBD
LAUNDRY | Cobalt Surfaces | Katanga Sand Dune K12-802 | Katanga Sand Dune K12-802 |  | 7x48 plank size
WALL TILE GROUT (SURROUNDS) | TBD | TBD | TBD | TBD | TBD

## TOILET ACCESSORIES
| Eagle Landing Southern Pines |  |  |  | Completed
TOILET ACCESSORIES | Scheme A & B |  | PLAN SPECS | PLAN SPECS | PLAN SPECS
DESCRIPTION | MANUFACTURER | FINISH | MODEL # | PHOTO | NOTES
TOWEL BAR and MOUNT | Trinsic | Arctic Stainless | 18" - 75918 24" - 759240 |  | Per 5/28 call, the descision to go chrome was made.
TOWEL RING | Trinsic | Arctic Stainless | 759460 |  | Per 5/28 call, the descision to go chrome was made.
ROBE HOOK | Trinsic | Arctic Stainless | 75935 |  | Per 5/28 call, the descision to go chrome was made.
TP HOLDER | Trinsic | Arctic Stainless | 75950 |  | Per 5/28 call, the descision to go chrome was made.
MIRROR |  | Plate Mirror with 1x4 Wood Trim attached in the Field, Painted Finish |  |  | Per Lowell in 6.4.20 mtg. - Paint the trim Proper Gray to match the cabinets.
SHOWER ROD |  | Chrome, Curved Rods |  |  | Per 5/28 call, the descision to go chrome was made.
SHOWER DOOR |  |  |  |  | Per 5/28 call, the descision to go chrome was made.

## DOORS AND HARDWARE
| Eagle Landing Southern Pines |  |  |  | Completed
DOORS + HARDWARE | Scheme A & B |  | PLAN SPECS | PLAN SPECS | PLAN SPECS
DESCRIPTION | MANUFACTURER | FINISH | MODEL # | PHOTO | NOTES
INTERIOR PRE-HUNG |  | Molded Wood Composite All Panel Interior Door | 5 Panel Style - per Owner selection |  | What Style Trim/Casing do you want for these doors? This will be for all interior door locations. THE PANEL STYLE SHOWN IN THE PHOTO IS FINE. VID ZDC would like to use the 5 panel door shown next to the single panel, but want the sharp edge look. (Shaker style panel, not the Raised Panel)
ENTRY DOOR | Masonite |  | Belleville Smooth Fiberglass, 2 Panel Square, 20 min rated |  | These are per plan styles. Is this what you want or something different? VID DID NOT DESIGN THE UNIT ENTRIES BUT THESE LOOK FINE.
LAUNDRY |  | Molded Wood Composite All Panel Interior Door | 5 Panel Style - per Owner selection
HVAC |  | Molded Wood Composite All Panel Interior Door | Louvered per Plan
PATIO | Masonite |  | HD Flush, Steel, Full View with 2-12", 2 Lite Transom above |  |  | Per 5/28 call, the descision to go chrome was made.
FRONT DOOR LEVER | Pamex | Chrome | Onyx, FLS Series |  | http://www.pamexinc.com/pamex-locks/onyx-contemporary-leverset | Per 5/28 call, the descision to go chrome was made.
FRONT DOOR LEVER FOB Lock needed correct? | YES NEED TO DECIDE BRAND AND INTERFACE SYSTEMS 5.1.20 | Chrome |  |  | What type of door lock do you want to have? OWNER WILL NEED TO CONFIRM WHAT WILL WORK WITH THEIR SYSTEM. VID | Per 5/28 call, the descision to go chrome was made.
PATIO DOOR LEVER | Delaney | Chrome | Vida |  |  | Per 5/28 call, the descision to go chrome was made.
INTERIOR DOOR LEVER - Privacy | Delaney | Chrome | Vida |  |  | Per 5/28 call, the descision to go chrome was made.
INTERIOR DOOR LEVER - Passage | Delaney | Chrome | Vida |  |  | Per 5/28 call, the descision to go chrome was made.
DEADBOLT Patio door?? | Thumb Turn with Blank back cover (6.4.20) |  |  |  |  | Per 5/28 call, the descision to go chrome was made.

## INTERIOR TRIM
| Eagle Landing Southern Pines |  |  | Completed
INTERIOR TRIM | Scheme A & B | PLAN SPECS | PLAN SPECS
DESCRIPTION | MATERIALS | NOTES | PHOTO | NOTES
UNIT BASE | 1 x 6 Flat Stock | Same as Union 198 |  | Flat 6"
UNIT DOOR CASING | 1 x 4 Flat Stock | Same as Union 198 |  | Flat 4"
UNIT WINDOW CASING | 1 x 4 Flat Stock | Same as Union 198 |  | Flat 4"
WINDOW RETURNS/JAMB EXTENSIONS | GWB | Same as Union 198 |  | Flat 4"
UNIT CROWN | 1 x 6 Flat Stock | **NEW** |  | ZDC would like Evolve to price crown in the living room/kitchen only. - 4.24.20 ***This was DELETED 2.5.21***
SHELVING |  | **Pricing the same style we did for 525 East (like brian did in my closet at home) |  | ZDC would like Evolve to look at a thicker pvc shelving in lue of white wire.
USB OUTLETS |  |  |  | 1 in kitchen near island and 1 in each bedroom near night stand. Robert Jones confirmed these ARE wanted, 1.11.21

## APPLIANCES
| Eagle Landing Southern Pines |  |  |  | Completed
APPLIANCES | Scheme A & B (all units) 188 total |  | PLAN SPECS - GE | PLAN SPECS - GE | PLAN SPECS - GE
DESCRIPTION | MANUFACTURER | FINISH | MODEL # | PHOTO | NOTES | NOTES
REFRIGERATOR all units | General Electric | Stainless Steel | GIE18GSHSS |  | 17.5 cf Top Freezer Refrigerator
REFRIGERATOR alternate pricing for all units | General Electric | Stainless Steel | GSE25GSHSS |  | 25.3 cf Side by Side, 36" wide, water in the door | ZDC wants for just the 3br units
RANGE | General Electric | Stainless Steel | JB645RKSS |  | 30" Free Standing, Ceramic Top, 5.3 cf, Self Clean
MICROWAVE | General Electric | Stainless Steel | JNM3163RJSS |  | 1.6 cf, 950 watt, Recirculating Vent
DISHWASHER | General Electric | Stainless Steel | GDF520PSJSS |  | Front Controls, 4 Cycles, 10 Options ***Discontinued***
DISPOSER | General Electric | Black | GFC325 |  | 1/3 HP Continous Feed
WASHER | General Electric | White | GTW680BSJWS |  | 4.6 cf, 14 Cycles, 6 Temperatures
DRYER | General Electric | White | GTD65EBSJWS |  | 7.4 cf, 12 Cycles, 4 Heat Selections

## Amenities
CLUBHOUSE FINISHES
| 0 |  |  |  | Completed/Approved
FLOORING SCHEME A (Gray Cabinets) | SCHEME A |  | PLAN SPECS | PLAN SPECS | PLAN SPECS
LOCATION | MANUFACTURER | STYLE | COLORS | PHOTO | NOTES
HWF -1 : Throughout Unless Otherwise Noted | Hurst Hardwoods | European French Oak | Arizona Engfoaz |  | 7.5" x 73" plank size (70% of area), Remainder to be 2'-4' lenghts Level 5 OK-10.1.20
CP-1: Clubroom Inset, Conference Room, Office, Leasing Inset | Atlas | Sumatra Shimmer IKAT | UM06 Offering |  | Level 5 OK-10.1.20
VF-1: Gym/Fitness | Chilewich |  | Plaid Grey |  | 18" x 18" Squares Level 5 OK-10.1.20
VF-2: Yoga | Chilewich |  | Plaid Tan |  | 18" x 18" Squares Level 5 OK-10.1.20
FT-1: Clubroom Kitchen Inset, Restrooms | Daltile | Keystones Custom 2 Sheet Pattern, File # 0928 | Arctic White: D617; Black: D311 |  | Grout: Mapei 10 Black Size: 1" x 1" Level 5 OK-10.1.20
WT-1: Leasing, Coffee Station, Cyber Café | Daltile | Lungarno Ceramics | Oro Pennyround Simoropnyrd |  | Grout: Mapei Avalanche 38 Size: Mosaic Level 5 OK-10.1.20
WT-2: Clubroom Kitchen | Fireclay Tile | Glazed thin brick | Cascade (VI) |  | Grout: Mapei Biscuit 14 Size: 2.5" x 8" Level 5 OK-10.1.20
WT-3: Clubroom Fireplace Surround and Accent Wall | Daltile | Panoramic Porcelain | Calacatta Glossy, CM04 |  | Grout: Mapei Frost 77 Size: 63" x 126" Slab Level 5 OK-10.23.20
WT-4: Restroom Accent Walls | Daltile | Keystones Custom 2 Sheet Pattern, File # 0928 | Arctic White: D617; Black: D311 |  | Grout: Mapei 10 Black Size: 1" x 1" Level 5 OK-10.1.20
KITCHEN QUARTZ | Silestone Cosentino | Charcoal Soapstone 808 1110203 Suede
LEASING DESKS/COFFEE STATION | Compac Surfaces | Carrara - Glace |  |  | Level 5 OK-10.23.20
POOL HOUSE - Vanity Faucets | Moen | T6193BG | Brushed Gold |  | Level 5 Selections
POOL HOUSE - Vanity Lights | Mitzi - Paige | H193303-AGB | Aged Brass |  | Level 5 Selections
POOL HOUSE - Paint | Sherwin Williams | SW7003 | Toque White |  | Level 5 Selections
POOL HOUSE - Vanity Countertops | Silestone Cosentino | Desert Silver | Polished |  | Level 5 Selections
POOL HOUSE - Bath flooring | Daltile | Emerson Wood | Hickory Pecan, EP05, 6 x 48 |  | Level 5 Selections
POOL HOUSE - Dog wash Wall Tile | Daltile | Color Wheel, 4 x 12 | Matte Artic White, Matte Black, and Bullnose |  | White to 5', then 1 course of Black, and cap with Bullnose White
POOL HOUSE - Dog wash Light | Mitzi - Cadence | H368601M-Blk/GL | Black and Gold |  | Level 5 Selections
POOL HOUSE - Cabana Pendant | Circa | Darlana , Medium wide hanging lantern | Bronze |  | Level 5 Selections
CLUBHOUSE - Fireplace | Town and Country | WS54 See Thru | Black Porcelain with Longbeach Log Set |  | Level 5 Selections

## PAINT
| Eagle Landing Southern Pines |  |  |  | Completed
PAINT | Scheme A (Gray Cabinets) 68 total | PLAN SPECS | PLAN SPECS | PLAN SPECS
LOCATION | DESCRIPTION | COLOR | PHOTO | NOTES
CEILING | Interior | Untinted White |  | SHERWIN WILLIAMS OR SIMILAR IS FINE. | Untinted White Flat per 5/28 call.
WALLS | Interior | SW7003 Toque White |  | SHERWIN WILLIAMS OR SIMILAR IS FINE. | Approved by Level 5 - Toque White
TRIM and Doors | Interior | SW7004 Snowbound Satin Finish |  | SHERWIN WILLIAMS OR SIMILAR IS FINE. | Approved by Level 5 - Snowbound Satin Finish
PAINT - (Per Rendering) | Exterior Wall Paint | SW7562 Roman Column |  |  | Per dropbox sent 5/1/20

## Submittals
SUBMITTALS
ITEM | RFP SENT DATE to Designer | PROPOSAL RECEIVED DATE | PROPOSAL APPROVED DATE | APROVED BY | NOTES
CABINETS
COUNTERTOPS
FLOORING/TILE
HARDWARE
PLUMBING
LIGHTING | 8.19.20
DOORS
MILLWORK
APPLIANCES
PAINT